## Sheet1
TK1.1 Critically evaluate the governance rules for investment appraisal | TK1.1 – Inclusion of a change control process | TK1.1 Establishing a schedule of project reviews | TK1.1 Establishing a schedule of project reviews | TK1.1 Critically evaluate different leadership styles. | TK1.1 Identify risks and capture issues
within or outside | variations, baseline, CCP aligns this with governance structures and organisational strategy | internal and external stakeholder needs | internal and external stakeholder needs | balance push and pull techniques | projects
potential value, business case | traceable decision making – delegated authority, accountability, auditability (=transparency for SH) | safety | safety |  | assumptions, unique, and constrained
robust justification for committing limited resources | benefit realisation chances, before/while escalating/rebaselining | performance | performance | aim = get best out of all at all levels via 2 way feedback | opportunities and threats
(delegated) authorisation and escalation/approval levels/limits apply | undermines cost, schedule, quality baselines, affect entire departments' operations | quality audit (by independent body) | quality audit (by independent body) | [Situational leadership model] | not include H&S risks
structure, consistency and strategic alignment | sponsors to make better decisions | Risks & issues | Risks & issues | - instructing/directive: commanding, sharp [in critical situations] | Brainstorming: With or without SH
Bureaucracy |  | escalation/change control with/to the reviewers (at least PM and sponsor) | escalation/change control with/to the reviewers (at least PM and sponsor) | - persuading/mentoring/coaching: when time for team dvpt | Checklists: of key company-wide issues
Inflexibility | TK1.2 – Capturing and recording change requests | Time: programme progress, delays, trends | Time: programme progress, delays, trends | - democratic/encouraging/engaging/facilitation: two way feedback with autonomy, also slow - team involved in decision making | Prompt list: Aide memoire using headings link to generic sources of risks
Over-reliance on quantitative data |  | continuous learning and cross pollination | continuous learning and cross pollination | - trusting/delegating: [for skilled/motivated team, need to know starting level] | SWOT PESTLE (for categorisation) analysis
Optimism bias | reviews: risk, schedule, cost – deviation from tolerated variance | Integrated Baseline Reviews (IBR - macro review...) | Integrated Baseline Reviews (IBR...) |  | can reduce weaknesses and threats
"Gaming the system" | change request form, clear, standardised | benefits/after action (6-12 months after handover | benefits/after action (6-12 months after handover | - servant leadership: well being of team = focus, can lack authority in high pressure situations | organisational level?
Misaligned incentives | change log/register, (5 options with +/-) | reviews carried out to date and further improvement | reviews carried out to date and further improvement | - transactional: clear roles/rewards, for compliance/time critical. Low innovation | Pre-mortem
approvers who critically challenge vs tick box |  | sponsor | sponsor |  | wide range of people and methods
sponsor usually secures funding | TK1.3 – High-level impact of a proposed change | align with governance and life cycle | align with governance and life cycle | - Confidence/ability model: support and instruction for nervous low ability, neither for confident and high ability, instruction for confident , support for high ability | robust analysis
finance expert |  | decision gates | decision gates |  | Facilitators
external funding often comes with costs | Generic Impact Assessment: SMEs/key SH, working assumptions, Iterative estimation | stage | stage | TK1.2 Critically analyse the behaviours and interpersonal skills that underpin effective leadership. | register with planned responses
long projects | risk and opp assessment techniques | peer | peer |  | description, cause, probab, impact, mitigation, fallbacks, status and responsible owners (person best placed
interest and exchange rate variations | benefits, cost (CB analysis), time, quality, resource & dependencies (scenario anal.) |  |  | - goal/vision (/standard setting) | (shared) system rather than manual spreadsheet
|  |  |  | - delegating (-> dvpt) | Separating Cause, event and effect helps reduce bias
TK1.2 Critically analyse ways in which organisations might release project funding | TK1.4 – Justifying approval, rejection, or deferral |  |  | - coaching, supporting, developing (teaching how to learn, knowing how)
|  | TK1.2 Sources of data to inform reviews | TK1.2 Sources of data to inform reviews | - feedback-giving (basis for learning)
decision gates, milestones | compare change against BC, benefits realisation plan and portfolio/strategy alignment/fit |  |  | - motivating others (<XP and vision)
delivery or handover | decision gate criteria, risk appetite and contingency availability | relevance | relevance | - influence and persuade (for int/ext SH who are unsure) | TK1.2 Techniques to assess risk
procurement, contractual dates | SH influence/own some of the reqs | needs/type | needs/type | - emotional intelligence and communication
scheduled drawdown dates | Quantitative aspect (cost/benefit, NPV, earned value) | informs data needs vs excessive/irrelevant/untimely data | informs data needs vs excessive/irrelevant/untimely data | - adaptability (especially vs conflict) | qualitatively indicates relative significance and any links and prioritise
risks become realised, mitigated |  | Depends on attendees: sponsor, project manager, governance board/management, PMO, specialists who are able to provide good challenge | Depends on attendees: sponsor, project manager, governance board/management, PMO, specialists who are able to provide good challenge | - reliability -> trust | likelihood and impact (cost, schedule, benefits, other benefits/risks)
contingency mgt, use if necessary | TK1.5 – Communicating outcomes | multiple sources | multiple sources | - decision making and judgement | Sufficient for many projects
known risks, reserves for unknown issues |  | internal | internal |  | risk owners and stakeholders contribution increases reliability
untouched and insufficient contingency show lack of risk alignment | openness and alignment with SH, Ethical thing to do and aligns with audit and assurance processes | external | external | TK1.3 Critically evaluate how understanding a project environment affects the leadership style. | Quantitative risk analysis (5v5 grid
if reserves are not sufficient, cost change control | continuous improvement – organisational knowledge management | primary | primary |  | a/ calculation of combined risk on objectives
| informed decisions, re baseline plans and budgets promptly | secondary/indirect | secondary/indirect | - Understand Project context: PESTLE, VUCA, SWOT | b/ implement pre agreed or ad hoc approach
|  | up to date and valid | up to date and valid | - Size: More strategic/long term & people focused on major, smaller more task/situational | numerical risk management
TK1.3 Critically evaluate the characteristics of a consistent approach to estimating | TK1.6 – Applying an approved change | validated through stakeholder/peer reviews, source verifications or simulations/testing | validated through stakeholder/peer reviews, source verifications or simulations/testing | - env changes (SH reqs, regs, market) require agility and rapid decision making | Monte Carlo simulation - probabilistic analysis - predicts combined effect
|  | baseline data should be frozen | baseline data should be frozen | - local and org culture form part of env and influence. In turn PM can improve company culture through trust, openness and psychological safety. | estimate of hitting dates, costs or benefits
time, resource and costs | formal authorisation |  |  | - remote teams: communication and feedback to create and guide towards a common sense of purpose | contingency to hold
for appraisal, for planning, for budget/affordability setting or for contingency planning | update the baselines for each |  |  | - 'survival' skills, honed with experience and knowledge: anticipation, judgement (people, potential issues), decision making | quality of input
more accurate with time as detailed information becomes available. Noting any assumptions will always help | communicate |  |  |  | Decision Trees
top-down (analogous/comparative [like for like], parametric [historical data + variables]) or bottom-up (analytical [component parts], Delphi [Subject Matter Experts for each subsystem]) often a combination | review change as part of continuous improvement and benefits review | TK1.3 Aligning reviews with governance processes | TK1.3 Aligning reviews with governance processes | TK1.4 Critically analyse the structure and content of a project vision and its importance. | Sensitivity Analysis
judgement | configuration control to ensure outputs match approved specs |  |  |  | which factors
innovative projects there will be little data |  | compliance with internal policies, regulatory requirements and industry standards | compliance with internal policies, regulatory requirements and industry standards | - why we are doing the project: regular, open, honest (repeated) comms | influence
guidance and training | TK1.7 – Patterns of change and trend analysis | non compliance, fines and legal issues | non compliance, fines and legal issues | - kick off/team/sponsor briefings to reinforce message
improve consistency between similar types of projects and within departments/organisations |  | quality assurance | quality assurance | - tailoring to teams/members of teams so they can understand their contribution in the bigger picture?
| statistical trend analysis (below), moving averages, regression analysis, comparative analysis | business case | business case | - Purpose/objectives(linked to org ones 'strategic alignment' ), scope, boundaries, value proposition, success criteria, SH impact
| PM to then characterise the trend – direction, strength | change in cost and benefits | change in cost and benefits | - All summarised in short statement, core values, goal | TK1.3 Types of impact risks and issues could have
| descriptive, diagnostic, predictive | closure if needed | closure if needed | - clear, simple, as/inspirational language: sense of purpose &excitement
TK1.4 Critically evaluate the range of metrics which can determine the value of a project to an organisation | limitations: bias in interpretation, size of sample | work is well managed | work is well managed | - Vision should be North Star to constantly guide decision making, team and SH engagement, scope control/change | Scope/Requirements
| verification, identified or suspected | wider business transparency and control | wider business transparency and control |  | change control
return on the organisation's investment |  | continuous improvement | continuous improvement | TK1.5 Critically evaluate methods for addressing challenges within a project environment | Schedule and Resource
must always be justified |  |  |  |  | late project completion or may require a cash injection/scope change
limited funds for groups of opportunities |  |  |  | - proactive: communication (more if remote), particularly of the (common) vision and purpose | Financial
simpler Rol |  |  |  | - active listening, behaviour awareness, openness, structured problem solving rather than blame | cost change control
Net Present Value seeks to calculate TVM. It accounts for opportunity and interest costs using discounted cash flows |  | TK1.4 Reporting and responding to project deviations | TK1.4 Reporting and responding to project deviations | - cultural/language barriers to be considered as early as possible | curtail scope or quality
see whether expected value is positive |  |  |  | - reactive: spelling out the issue with the (1 or +) parties. Set clear expectation, draw on different leadership styles depending on knowledge of the challenged/ing partie/s. firmness&empathy | Technical
can be assisted by software |  | Identify | Identify | - levels of problem: from mild annoyance to illegal behaviour. Some things to report immediately and not PM job to resolve. | very difficult, time-consuming and costly to rectify
Internal Rate of Return is the average per period rate of return on capital invested, the discount rate giving a 0 NPV |  |  |  | - collaboration with all/any relevant parties rather than | External
hurdle rates |  | Deviation from baseline | Deviation from baseline | - realise limitations of conflict resolution at local level - escalate through management or HR. | Regulatory changes, market shifts, natural disasters, political instability, new laws, third-party contractor failure
can also account for risk, margin currency exchanges, effectively by discounting the IRR based on forecast effect of key financial risks |  | schedule | schedule | - Stress - Yerkes Dobson law: humans perform best halfway between sleep state and total panic. Monitor levels in team particularly on intense projects. | fines, major delays, project shutdowns or require significant changes
Weighted Average Cost of Capital (WACC) uses company/project equity and debt to work out minimal hurdle rate required |  | budget | budget |  | obsolete
portfolio level |  | scope | scope
|  | tolerance levels | tolerance levels
|  | Identify deviations by monitoring progress, tracking KPIs, EVM, auditing quality and managing risks. Evidencing | Identify deviations by monitoring progress, tracking KPIs, EVM, auditing quality and managing risks. Evidencing
|  | reports | reports |  | TK1.4 Techniques to improve issue management through continuous improvement
TK1.5 Critically analyse the information expected to be available for financial reviews |  | cause | cause
|  | risk register | risk register |  | continuous Improvement involves gathering performance data (quant and qual), analysing it and implementing identified improvements
once have budget and cash flow forecast |  | team/stakeholder feedback and communication | team/stakeholder feedback and communication |  | Shewhart/Deming Cycle (Plan Do Check Act)
actual expenditure tracking |  |  |  |  | structured, and infinitely enhancing
accounting systems to get figures, finance experts? |  | Respond | Respond |  | six sigma: enables root cause identification
exceed budgets calls the PM to intervene |  |  |  |  | DMAIC for existing processes
rolling forecast into the future, possibly divided into financial control periods |  | control, transparency and timely correction | control, transparency and timely correction |  | Define
deviations between previous forecast and latest actuals |  | variance reports | variance reports |  | Measure
backward looking explanations for deviations |  | root cause analysis: 5 whys | root cause analysis: 5 whys |  | Analyse
|  | prevents recurrence BUT requires time, expertise, and resources | prevents recurrence BUT requires time, expertise, and resources |  | whyx5
Improve
Control
TK1.6 Critically evaluate tools and techniques available to monitor and analyse the financial performance of a project |  |  |  |  | DMADV for new processes: Define, Measure, Analyse, Design, Verify
|  | TK1.5 Stakeholder involvement in review outcomes | TK1.5 Stakeholder involvement in review outcomes |  | ITIL Continual Service Improvement - seeks to prevent issues
excel for raw cost data or erp/SAP (Accounting figures - cash or accrual method (matching principle) +/-) |  |  |  |  | 7 step process for managing IT related issues
consider cost and schedule performance at the same time |  | internal: sponsor, client, team members, PMO, (programme) manager | internal: sponsor, client, team members, PMO, (programme) manager |  | Logs Known errors
forecast creation based on current performance: estimate to and at completion, cost and schedule variance, cost and schedule performance index |  | external: suppliers, regulatory bodies + local gvt & businesses | external: suppliers, regulatory bodies + local gvt & businesses
requires cost loaded programme and huge amount of work - possibly pmo job |  | identified and mapped | identified and mapped
requires reliable info which should be readily |  | involved | involved
cost loaded p6/similar programme also accounts for time |  | improves engagement - expectation meeting | improves engagement - expectation meeting |  | TK1.5 Need for ongoing ownership of risks
More instinctive, less training required |  | brainstorming workshops or public meetings | brainstorming workshops or public meetings
|  | Participatory reviews | Participatory reviews |  | show support and collaboration for proper institutional management of risk
|  | validate data/information/perception | validate data/information/perception |  | not assigned
|  | sign off on approvals | sign off on approvals |  | likely to fall through cracks
|  | managed and targeted | managed and targeted |  | risks need to be monitored from capture to ALARP mitigation or project close out
|  | co-creation | co-creation |  | roles rather than names
|  | high power, high interest groups | high power, high interest groups |  | workflow software
huge project
focus on higher impact risks
clear responsibilities, instructions/language
|  | TK1.6 Actions for re-planning after deviations | TK1.6 Actions for re-planning after deviations |  | training if necessary
resist temptation to give bulk of risks to really senior people
|  | Risk becomes issue: Consider contingency/action plans | Risk becomes issue: Consider contingency/action plans |  | have time, money and resources needed
|  | escalation | escalation |  | shifting from an 'old school' culture
|  | resources may need to be reallocated | resources may need to be reallocated |  | easier/quicker to address issues
|  | impact other tasks | impact other tasks
|  | rescheduling/re baseline | rescheduling/re baseline
|  | critical tasks | critical tasks
|  | config/scope change | config/scope change
|  | cost change control | cost change control
|  | root cause | root cause
|  | decision gates | decision gates
|  | unable to meet its objectives | unable to meet its objectives
|  | no longer aligned | no longer aligned
|  | no longer a viable business case | no longer a viable business case
|  | end all or part | end all or part
|  | TK1.7 Why planned reviews might need to change | TK1.7 Why planned reviews might need to change
|  | based on a baseline of scope /cost /programme /resources | based on a baseline of scope /cost /programme /resources
|  | Internal and external changes | Internal and external changes
|  | emergence of risk esp unknown external | emergence of risk esp unknown external
|  | Stakeholder reqs | Stakeholder reqs
|  | different reviews | different reviews
|  | different attendees, frequency, additional floating stage gate? external audit? different focus in reviews? | different attendees, frequency, additional floating stage gate? external audit? different focus in reviews?
|  | TK1.8 Impact of reviews on business case and wider organisation | TK1.8 Impact of reviews on business case and wider organisation
|  | Business Case | Business Case
|  | refinement of objectives | refinement of objectives
|  | risk/op management | risk/op management
|  | cost/benefit reassessment to revalidate the BC | cost/benefit reassessment to revalidate the BC
|  | decision gates enable budget cuts, restructuring or cancellation | decision gates enable budget cuts, restructuring or cancellation
|  | protect future BCs by learning lessons | protect future BCs by learning lessons
|  | Wider organisation | Wider organisation
|  | ensure alignment between project and wider strategy | ensure alignment between project and wider strategy
|  | Feeding back | Feeding back
|  | wider strategy to be refined | wider strategy to be refined
|  | culture | culture
|  | processes | processes
|  | resources to be considered on a organisational level | resources to be considered on a organisational level
|  | stakeholder and leadership engagement | stakeholder and leadership engagement