## Sheet1
TK1.1 – Inclusion of a change control process
variations, baseline, CCP aligns this with governance structures and organisational strategy
traceable decision making – delegated authority, accountability, auditability (=transparency for SH)
benefit realisation chances, before/while escalating/rebaselining
undermines cost, schedule, quality baselines, affect entire departments' operations
sponsors to make better decisions
TK1.2 – Capturing and recording change requests
reviews: risk, schedule, cost – deviation from tolerated variance
change request form, clear, standardised
change log/register, (5 options with +/-)
TK1.3 – High-level impact of a proposed change
Generic Impact Assessment: SMEs/key SH, working assumptions, Iterative estimation
risk and opp assessment techniques
benefits, cost (CB analysis), time, quality, resource & dependencies (scenario anal.)
TK1.4 – Justifying approval, rejection, or deferral
compare change against BC, benefits realisation plan and portfolio/strategy alignment/fit
decision gate criteria, risk appetite and contingency availability
SH influence/own some of the reqs
Quantitative aspect (cost/benefit, NPV, earned value)
TK1.5 – Communicating outcomes
openness and alignment with SH, Ethical thing to do and aligns with audit and assurance processes
continuous improvement – organisational knowledge management
informed decisions, re baseline plans and budgets promptly
TK1.6 – Applying an approved change
formal authorisation
update the baselines for each
communicate
review change as part of continuous improvement and benefits review
configuration control to ensure outputs match approved specs
TK1.7 – Patterns of change and trend analysis
statistical trend analysis (below), moving averages, regression analysis, comparative analysis
PM to then characterise the trend – direction, strength
descriptive, diagnostic, predictive
limitations: bias in interpretation, size of sample
verification, identified or suspected